## Weekly Plan
Solo SaaS Weekly Replanning Worksheet
Plan within real capacity. Enter hours in the input cells; totals and variance calculate automatically.
Capacity calculation
Total work hours | 40 |  | Planned task hours
Fixed commitments (calls/admin) | 6 |  | Capacity remaining
Planned buffer | 6 |  | Capacity check
Available task capacity |  |  | Revised task hours
Revised capacity remaining
Revised capacity check
Task / work category | Priority (High/Med/Low) | Planned hours | Actual hours | Variance (Actual − Planned) | Next-week action | Revised hours
Tip: Add tasks as rows. Compare the total planned hours with available task capacity before committing.
Next-week check: adjust B5:B7 for next week, then make sure revised task hours fit within the available capacity.

## Actual Work Log
Actual Work Log
Record work as it happens. Use one row per task or work session; this log helps improve future estimates.
Date | Task / activity | Category | Hours spent | Notes / interruption

## Replanning Decisions
Replanning Decisions
Turn last week's actuals into explicit decisions for the next week. Avoid carrying every unfinished task forward automatically.
Task | What happened / evidence | Priority | Decision | Revised hours | Target week / next step

## Read Me
How to Use This Worksheet
A lightweight weekly replanning loop for solo SaaS founders. Example values are illustrative—replace them with your own data.
1. Set capacity | Enter total work hours, fixed commitments and a realistic buffer in Weekly Plan. Available task capacity is calculated automatically.
2. Plan the work | Add key tasks and planned hours. Keep the total planned hours at or below available task capacity.
3. Log actuals | Use Actual Work Log during the week. Track meaningful categories; you do not need to time every tiny action.
4. Compare | Transfer actual hours for each planned task to Weekly Plan. Variance is Actual − Planned; positive means over estimate.
5. Make decisions | In Replanning Decisions, choose Keep, Move, Reduce, Drop or Add. Give moved tasks a specific target week.
6. Rebuild next week | Update capacity and estimates based on repeated patterns, not a single unusual week. Preserve some buffer.
Capacity formula | Available task capacity = total work hours − fixed commitments − planned buffer.
Variance formula | Variance = actual hours − planned hours.
Important | This worksheet is a planning aid, not a performance score. An overrun may reflect an urgent incident or a poor estimate; interpret it in context.
Note on logging | The Actual Work Log is a separate record. Transfer weekly totals into the Actual hours column on Weekly Plan; they do not auto-populate.